## google shhet ko aur advance goo
Day | Main Goal | Tasks | Status | Progress Notes
Day 1 | Setup and Data Ingestion | Install VirtualBox & Linux VM Install Apache2 & Splunk UF Install Splunk Enterprise Connect UF to Splunk Enterprise Input Apache & Linux system logs | TRUE
Day 2 | Data Parsing & Normalization | Search and verify log data Use rex to extract key fields (e.g., client_ip, status_code) Save field extractions as Knowledge Objects Create a saved search for common errors | TRUE
Day 3 | IT Ops Monitoring Dashboard | Create a new Dashboard: "IT Operations Add a chart for HTTP Status Codes Add a chart for Requests per minute Create a table for Top 10 Requested URLs</li></ul> | TRUE
Day 4 | Security Analytics Dashboard | Create a new Dashboard: "Security Threat" Add a table to track failed login attempts from auth.log Add a chart for unusual activity (e.g., high rate of 404 errors) Use an IP lookup command to show attacker locations on a map | TRUE
Day 5 | Alerts & Advanced Search | Set up an alert for multiple failed logins from one IP Set up an alert for suspected port scanning activity Practice streamstats and transaction commands | TRUE
Day 6 | Reporting & Documentation | Create a weekly summary report of dashboard metrics Write a short project summary (objective, process, results) Prepare screenshots of key dashboards | TRUE
Day 7 | Final Review & Presentation Prep | Review all dashboards and alerts for accuracy Practice presenting the project in a mock interview setting Prepare to discuss challenges faced and solutions applied | FALSE